## Task
No. | FunctionID | Function Name | Task | PIC | Plan Effort (hour) | Actual Effort (hour) | Progress | Status | Plan |  | Actual |  |  | On time | Note
[9 empty] | Start | End | Start | Plan End | End
WEEK 1
1 | MC001 | Meeting client | Meeting client at personal lab to kick-off the project | All | 6 | 6 | 100% | Done | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | Yes | 9AM at personal house (Abscent: Duy)
2 | KO001 | Create workspace | Create GitHub account for team | Thanh | 2 | 2 | 100% | Done | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | Yes
3 | KO001 | Create workspace | Create communication channels for team (slack,fb group,google drive,email...) | Hoang, Tu, Phuong | 3 | 3 | 100% | Done | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | Yes
4 | KO001 | Create workspace | Create project & build source code | Duy | 1 | 1 | 100% | Done | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | Yes
5 | SM001 | Summarize | Summarize customer's requirement and export backlog file | Hoang | 4 | 4 | 100% | Done | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | Yes | check #document in Slack
WEEK 2
MID-TERM EXAM
WEEK 3
6 | RD001 | Read document | Read: how to make a project plan and making plan for 1st week | Thanh | 2 | 2 | 100% | Started | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes | read GSD_Schedule in Plan folder
7 | RD001 | Read document | Read document | Thanh | 8 | 8 | 100% | Started | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes
8 | RD001 | Read document | Read document | Phuong | 8 | 8 | 100% | Started | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes
9 | RD001 | Read document | Read document | Duy | 8 | 8 | 100% | Started | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes
10 | RD001 | Read document | Read document | Tu | 8 | 8 | 100% | Started | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes
11 | RD001 | Read document | Read document | Hoang | 8 | 8 | 100% | Done | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes
12 | FL001 | Draw flow | Draw flows for some processes | Hoang | 8 | 8 | 100% | Done | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-28 | Yes | Qtkykethopdong.doc, QTLaymau.doc, Qtchuyengiaoluutruthanlymau.doc
13 | S001 | Search template | Search template for administration page | Duy | 1 | 0.5 | 100% | Done | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-26 | Yes | https://marketplace.visualstudio.com/items?itemName=LuisErnestoVasquez.ASPMVC5withsbadmin2bootstraptemplate
14 | MC001 | Meeting client | Have an appoinment with clients to discuss further about the project at IER (process,etc...) | All | 5 | 5 | 100% | Done | 2016-11-25 | 2016-11-30 | 2016-11-25 | 2016-11-30 | 2016-11-30 | Yes | 8:00AM at US (Abscent: Duy, Tu)
15 | W001 | Write user story | Describe user story and their functions for some processes | Thanh | 3 | 3 | 100% | Done | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | Yes | Qtkykethopdong.doc, QTLaymau.doc, Qtchuyengiaoluutruthanlymau.doc
16 | W001 | Write user story | Describe user story and their functions for some processes | Duy | 3 | 3 | 100% | Done | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | Yes
17 | W001 | Write user story | Describe user story and their functions for some processes | Tu | 5 |  |  | Not Done | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 |  | No
WEEK 4
18 | KO001 | Sharing | Share project and help other teammates setup environment | Duy | 2 | 2 | 100% | Done | 2016-12-01 | 2016-12-03 | 2016-12-01 | 2016-12-03 | 2016-12-03 | Yes
19 | F001 | User management | User list | Duy | 1 | 1 | 100% | Done | 2016-12-01 | 2016-12-03 | 2016-12-01 | 2016-12-03 | 2016-12-03 | Yes
20 | F002 | User management | Add new user | Duy | 1 | 1 | 100% | Done | 2016-12-01 | 2016-12-03 | 2016-12-01 | 2016-12-03 | 2016-12-03 | Yes
21 | F003 | User management | Update user | Duy | 1 | 1 | 100% | Done | 2016-12-01 | 2016-12-03 | 2016-12-01 | 2016-12-03 | 2016-12-03 | Yes
22 | F004 | User management | Delete user | Duy | 1 | 1 | 100% | Done | 2016-12-01 | 2016-12-03 | 2016-12-01 | 2016-12-03 | 2016-12-03 | Yes
23 | RE001 | Review | Review user's requirement and discuss about the prototype | Thanh, Phuong, Hoang, Duy | 6 | 6 | 100% | Done | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | Yes
24 | D001 | Draw flow | Draw prototypes for all users (related to QuyTrinhLayMau) in draft paper | Thanh, Phuong, Hoang | 8 | 8 | 100% | Done | 2016-12-07 | 2016-12-09 | 2016-12-07 | 2016-12-09 | 2016-12-09 | Yes
25 | DL001 | Download tool | Download application used to draw prototype on computer | Tu | 2 | 2 | 100% | Stared | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | Yes
26 | RE001 | Review | Review task 24 | Phuong, Hoang | 4 | 4 | 100% | Started | 2016-12-09 | 2016-12-11 | 2016-12-09 | 2016-12-11 | 2016-12-11 | Yes
WEEK 5
27 | D001 | Draw flow | Fix prototype for all users | Thanh,Phuong,Hoang | 2 | 2 | 100% | Done | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | Yes | 13h-15h at Lab
28 | TP001 | Transfer | Redraw all prototypes in computer | Phuong | 6 | 6 | 100% | Done | 2016-12-11 | 2016-12-12 | 2016-12-11 | 2016-12-12 | 2016-12-12 | Yes
29 | DE001 | Design | Design database for "QTLayMau" & "QTNhanMau" | Hoang | 6 | 6 | 100% | Done | 2016-12-13 | 2016-12-14 | 2016-12-13 | 2016-12-14 | 2016-12-14 | Yes
30 | RE001 | Review | Review Task 29 | Phuong | 2 | 2 | 100% | Done | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | Yes
31 | W001 | Write document | Write document for presentation on Thursday | Thanh | 3 | 3 | 100% | Done | 2016-12-12 | 2016-12-14 | 2016-12-12 | 2016-12-14 | 2016-12-14 | Yes
32 | RE001 | Review | Review + modify task 31 | Phuong | 3 | 3 | 100% | Done | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | Yes
33 | MC001 | Meeting client | Meeting client at personal lab in Thu Duc | All | 5 | 5 | 100% | Done | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | Yes | 1PM at Ho Con Rua
34 | CODE001 | Code | Form 14.01, add "Loai" column to the table | Hoang | 4 | 4 | 100% | Done | 2016-12-16 | 2016-12-21 | 2016-12-16 | 2016-12-21 | 2016-12-21 | Yes
35 | CODE001 | Code | Form 14.03, add "Ky hieu mau" column to the table | Phuong | 4 | 4 | 100% | Done | 2016-12-16 | 2016-12-21 | 2016-12-16 | 2016-12-21 | 2016-12-21 | Yes
36 | CODE001 | Code | Form 15.01, add "Nguoi giao", "Nguoi nhan", "Dien ten" columns to the table | Thanh | 4 | 4 | 100% | Done | 2016-12-16 | 2016-12-21 | 2016-12-16 | 2016-12-21 | 2016-12-21 | Yes
37 | CODE001 | Code | Form 19.01, 19.02 | Tu | 8 | 8 | 100% | Done | 2016-12-16 | 2016-12-21 | 2016-12-16 | 2016-12-21 | 2016-12-21 | No | Completed by another member
38 | CODE001 | Code | Tinh tien, Bang bao gia | Duy | 8 | 8 | 100% | Done | 2016-12-16 | 2016-12-21 | 2016-12-16 | 2016-12-21 | 2016-12-21 | No
WEEK 6
39 | W001 | Write document | Write proposal | Thanh | 3 | 3 | 100% | Done | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | Yes
40 | W001 | Write document | Prepare slide for presentation | Phuong | 3 | 3 | 100% | Done | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | Yes
Presentation
WEEK 7
FINAL EXAMINATION
WEEK 8
BREAK
WEEK 9
WEEK 10
| TM | Team meeting | Teem meeting at LAB | All | 3 | 3 | 100% | Done | 16/1/2017 | 16/1/2017 | 16/1/2017 | 16/1/2017 | 16/1/2017 | Yes | 11:30AM
| RE001 | Review | Review and fix all tables | Thanh, Hoang, Phuong | 4 | 4 | 100% | Done | 16/1/2017 | 16/1/2017 | 16/1/2017 | 16/1/2017 | 16/1/2017 | Yes
| CODE001 | Code | Code main funtions | Duy | 15 |  |  | Started | 2017-08-01 | 18/1/2017 |  |  |  | No
| CODE001 | Code | Code "Them mau vao yeu cau" | Hoang | 6 |  |  | Started | 18/1/2017 | 18/1/2017
| RE001 | Review | Review task | All | 2 | 2 | 100% | Done | 18/1/2017 | 18/1/2017 | 18/1/2017 | 18/1/2017 | 18/1/2017 | Yes
| CODE001 | Code | Create views,models and controllers for table | Thanh | 3 | 3 | 100% | Done | 18/1/2017 | 18/1/2017 | 18/1/2017 | 18/1/2017 | 18/1/2017 | Yes
| RES | Research | Research about ASP .NET MVC | Thanh | 5 | 5 | 100% | Done | 19/1/2017 | 19/1/2017 | 19/1/2017 | 19/1/2017 | 19/1/2017 | Yes
| CODE001 | Code | Code template for "" | Hoang | 4 | 4 | 100% | Done | 18/1/2017 | 18/1/2017 | 18/1/2017 | 18/1/2017 | 18/1/2017 | Yes
WEEK 11,12,13
TET HOLIDAY BREAK
WEEK 14
| CODE001 | Code | Fix tables templates | Thanh | 4 |  |  | Started | 2017-09-02 | 13/2/2017
| FIX | Fix prototype | Fix prototype | Phuong | 6 |  |  | Started | 2017-09-02 | 13/2/2017
| CODE001 | Code | Fix and complete task "CODE MAIN FUCTIONS" | Hoang, Duy | 6 |  |  | Started | 2017-09-02 | 13/2/2017