## Sheet1
Issue ID | Description | Status | Priority | Assign To | Assign Date | Root | Note | Tester/Checker
D01 | Error: some Models do not contain definition used in Views | Open | Critical |  |  | - deploy_fail_log_01a.png - deploy_fail_log_01b.png | I have solved this by remove never-used views | htaphuong
D02 | Error: some libraries have been removed but still happened in project folder | Open | High |  |  | - error_deploy_non-exists-lib.png - error_deploy_non-exists-lib02.png | Solved by removing them from project? Need to confirm | htaphuong